## Slide 1: Cignetti Turnaround
WW25 2026

## Slide 2: SUNPOWER DIRECT PROCESSES: TARGET TO FPY=100%
Author: JYH/EVV/ERF, 6/16/2026
Owner: ERF
Spec: 10009
T Level | Stage | Process Owner/ Quality | Milesone1 | to | Milestone2 | Level 2 | Level 3 | RCCA | Latest FPY
T0 | S1 | KXW/DJF | Booking | to | Project Received | 12885 | 10848 | 147, D8 | Investigating*
T0 | S2 | SGS/DJF | Project Received | to | Layout and Upgrade Review | 12777 | 12304 | 147, D8 | Investigating*
T0 | S3 | SGS/DJF | Layout and Upgrade Review | to | Project Huddle | 12777 | 12304 |  | Investigating*
T0 | S4 | SGS/DJF | Project Huddle | to | FDC (Project Acceptance) | 12777 | 10470 | 137, D8 | 63%
T1 | S5 | SGS/DJF | Final Design Complete | to | Permit Pack Completed | 12777 | 12385 | 138, D6 | Investigating*
T1 | S6 | PXA/DJF | Permit Pack Completed | to | Request Permit | 12759 | 10823 |  | 100%
 |  | PKN/EZD |  |  | IXP1 Submission | 12649 | 12460 |  | Investigating*
T1 | S7 | PXA/DJF | Request Permit | to | Permit Approved | 12649 | 12556 |  | 100%
 |  | PKN/EZD | IXP1 Submission | to | IXP1 Approval | 12649 | 12556 | 222, D1 | 100%
T1 | S8 | SAH/DJF | Permit Approved/IXP1 Approval | to | Ready To Schedule | 12783 | 10961 |  | Investigating*
T1 | S9 | SAH/ZJW | Ready To Schedule | to | Install Scheduled | 12783 | 11819 |  | Investigating*
T1 | S10 | IPG/ZJW | Install Scheduled | to | Substantial Completion Verified | 12022 | 10496 | 188, D6 | 70%
T2 | S11 | KMM/RJG | Substantial Completion Verified | to | M2 Install Submission (Parallel) | No Spec | 12285/12430 | 228, D4 | 97%
T2 | S12 | KMM/RJG | M2 Submission | to | M2 Install Approved (Parallel) | No Spec | 12285/12430 | 228, D4 | 98%
T2 | S13 | RLJ/ZJW | Substantial Complete | to | Final Inspection Scheduled | 12807 | 11001 | 187, D3 | Investigating*
T2 | S14 | RLJ/ZJW | Final Inspection Scheduled | to | Final Inspection Verified | 12807 | 10899 | 187, D3 | 68%
T3 | S15 | PKN/EZD | Final Inspection Verified | to | Permission To Operate | 12834 | 11143 |  | Investigating*
 |  | KMM/RJG | Permission To Operate | to | M3 Activation Approved | No Spec | 12445 | 234, D3 | 100%
T3 | S16 | MBC/TGM | Permission To Operate | to | Grant PTO To Customer | 13050 | 13049 |  | Investigating*
Source: 10009/N Section 5, page 14 (table)
* Salesforce Data gathering
Notes: Add links to the spec
Put RCCA stage (D1,D2,etc etc)

## Slide 3
Chart: SPWR DIRECT: FDC FIRST PASS YIELD FPY TARGET = 100%
| 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 2026
Volume | 116 | 103 | 119 | 125 | 118 | 166 | 140 | 75
FPY | 0.81897 | 0.73786 | 0.72269 | 0.712 | 0.71186 | 0.73494 | 0.70714 | 0.62667
Target | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Escalation | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97
SunPower Direct Final Design Complete FPY, WW25
Author: EVV, 6/22/2026 Owner: SGS / BCB QA: DJF
97%
Escalate to
SSB
SPEC 10470
RCCA 235, D1
(OPEN)
Spec 10470

## Slide 4
SunPower Direct Final Design Complete FPY, WW25
Spec 10470
RCCA 235. D1
(OPEN)
Author: EVV, 6/22/2026 Owner: SGS / BCB QA: DJF
Specs L2: 12777 Specs L3: 10470

## Slide 5
Chart: SPWR DIRECT, SCV FIRST PASS YIELD, CORP. QA AUDIT FPY TARGET = 100%
| 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17* | 18 | 19 | 20 | 21 | 22 | 23* | 24 | 25 | 2026
Volume | 37 | 19 | 27 | 19 | 30 | 21 | 11 | 7 | 15 | 18 | 16 | 20 | 20 | 17 | 17 | 16 | 20 | 15 | 20 | 16 | 10 | 16 | 22 | 20
FPY | 0.72973 | 0.78947 | 0.77778 | 0.84211 | 0.93333 | 0.95238 | 0.90909 | 1 | 1 | 0.94444 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95 | 1 | 1 | 1 | 0.86364 | 0.7
Target | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Escalation | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97
S10: SPWR Direct SCV Corporate QA Inspection, WW25
Data Source: TGM/ZJW/EVV, 6/22/2026
SPEC: 10496, RCCA: 188, D6 * WW17, WW23: Revised the FPY Data to 100% for spec alignment.
ROOT CAUSE CORRECTIVE ACTION
ANDON CORD ACTIVATED
1/27/2026, 3PM
SSB-164A
RCCA188, D6 (OPEN)
SPEC 10496
97%
Escalate to
SSB
TRAINING
TGM-74A
Missing Photos,
1 Submission
RCCA188, D6 (CLOSED)
Permit Set Mismatch, 1 Submission
RCCA188, D6 (CLOSED)
Electrical Defect, 1 Submission
RCCA188, D6 (CLOSED) TRAINING – CMM-50A
Tilt Photo,
1 Submission
RCCA188, D6 (CLOSED)
Blurry Photo, Permit Set Mismatch, Electrical Defect
3 Submission
RCCA188, D6 (CLOSED)
Electrical Defect
6 Submission
DON'T PUT RAW SEWAGE
IN THEIR COMPUTER
CONTAINMENT
ANDON CORD LIFTED 2/01/2026. 11:15AM Sunday
SSB-164B

## Slide 6
SPWR Direct S10 SCV Corporate QA WW52-WW25’2026
1Funding Defect: AVL LightReach eligibility, PV Panel mismatch, Missing Cell kit
2Electrical Defect: Main breaker/sub-panel issues, Point of interconnection issues
1
2
Data Source: TGM/EVV, 6/22/2026
Spec 10496
RCCA 195. D6
(OPEN)
RCCA 188. D6
(CLOSED)
RCCA 188. D6
(CLOSED)

## Slide 7
Chart: SPWR DIRECT FPY M1 SUBMISSION TO CORPORATE QA FPY TARGET = 100%
| 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 2026
N | 44 | 57 | 45 | 18 | 27 | 32 | 41 | 33
FPY | 0.63636 | 0.70175 | 0.68889 | 0.88889 | 1 | 1 | 0.90244 | 0.9697
Target | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Escalation | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97
SunPower Direct M1 Corporate QA Inspection, WW25
Author: RJG/EVV, 6/20/2026
Owner: KMM/AEP
SPEC 12285
ANDON CORD
RCCA 228, D6 (OPEN)
TRAINING
SPEC 12285
ANDON CORD 1
RCCA 228
97%
Escalate to
SSB
* Additional Quality Staff Deployed and checked before submission to Corporate QA
CONTAINMENT
*
*
WW24: FIELD, PCS Bundling, CT Issue, FUNDING CSLB Disclosure, Production Modelling. Decoder 2 KMM and 2 RYW
WW25: DESIGN: Electrical Issue. Decoder 1 RYW
4 REJECTS. RCCA 228, D6 (OPEN)
ADDITIONAL TRAINING
SPEC 12285, REV N UPDATE
INSPECTION UPSTREAM
REQUIRED FOR DESIGN AND FIELD
ROOT CAUSE CORRECTIVE ACTION
*
1 REJECT
ELECTRICAL ISSUE
(DESIGN)
Notes: Update to 25.1

## Slide 8
Chart: SPWR DIRECT FPY M1 SUBMISSION TO CORPORATE QA FPY TARGET = 100%
| 1 | 2 | 3 | 4 | 5 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 2026
N | 44 | 57 | 45 | 18 | 27 | 32 | 41 | 5 | 8 | 7 | 5 | 8
FPY | 0.63636 | 0.70175 | 0.68889 | 0.88889 | 1 | 1 | 0.90244 | 1 | 0.875 | 1 | 1 | 1
Target | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Escalation | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97
SunPower Direct M1 Corporate QA Inspection, WW25.5
Author: RJG/EVV, 6/20/2026
Owner: KMM/AEP
SPEC 12285
ANDON CORD
RCCA 228, D6 (OPEN)
TRAINING
SPEC 12285
ANDON CORD 1
RCCA 228
97%
Escalate to
SSB
* Additional Quality Staff Deployed and checked before submission to Corporate QA
CONTAINMENT
*
*
WW24: FIELD, PCS Bundling, CT Issue, FUNDING CSLB Disclosure, Production Modelling. Decoder 2 KMM and 2 RYW
WW25: DESIGN: Electrical Issue. Decoder 1 RYW
4 REJECTS. RCCA 228, D6 (OPEN)
ADDITIONAL TRAINING
SPEC 12285, REV N UPDATE
INSPECTION UPSTREAM
FOR DESIGN AND FIELD
ROOT CAUSE CORRECTIVE ACTION
*
1 REJECT
ELECTRICAL ISSUE
(DESIGN)
Notes: Update to 25.1

## Slide 9
SunPower Direct M1 Corporate QA Inspection, WW24-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM QA: RJG
Spec 12285
RCCA 228. D6
(OPEN)
* Additional Quality Staff Deployed and checked before submission to Corporate QA (from 21.2TD)
WW24: FIELD, PCS Bundling, CT Issue, FUNDING CSLB Disclosure, Production Modelling. Decoder 2 KMM and 2 RYW
WW25: DESIGN: Electrical Issue. Decoder 1 RYW

## Slide 10
SunPower Direct M1 Corporate QA Inspection, WW24-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Spec 12285
RCCA 228. D6
(OPEN)

## Slide 11
SunPower Direct M1 Corporate QA Inspection, WW19-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM QA: RJG
Spec 12285
RCCA 228. D6
(OPEN)
* Additional Quality Staff Deployed and checked before submission to Corporate QA (from 21.2TD)

## Slide 12
SunPower Direct M1 Corporate QA Inspection, WW19-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Spec 12285
RCCA 228. D6
(OPEN)
* Additional Quality Staff Deployed and checked before submission to Corporate QA (from 21.2TD)

## Slide 13
S14: SPWR Direct Final Inspection Verified FPY, WW18-WW25
Data Source: Salesforce/EVV, 6/22/2026 Owner: RLJ QA: TGM, ZJW
SPEC 12807
RCCA 187, D3
(OPEN)
97%
Escalation
to SSB
*
**
* ANDON CORD FOCUSED ON CREW FROM IL & MI – ZJW-30A
* WW20-24 Data Under Validation with RLJ (FIV Team)

## Slide 14
Chart: PARETO ANALYSIS
| Uncategorized* | AHJ | ET | Design | Inspections | Customer | Permitting | FOT | Crew | ST | IP | Installs | Supply Chain | Quality Control
Distinct Count of Project Name | 74 | 34 | 16 | 15 | 12 | 9 | 7 | 5 | 4 | 3 | 2 | 2 | 1 | 1
%Cumulative | 0.13362 | 0.39655 | 0.48563 | 0.60776 | 0.71552 | 0.77011 | 0.83046 | 0.87356 | 0.91523 | 0.94684 | 0.96839 | 0.9842 | 0.99569 | 1
SPWR Direct S14 Final Inspection Verified Pareto, WW18-WW25
* WW20-25 Data Under Validation with RLJ (FIV Team)
1
2
3
4
5
6
Spec 12807
RCCA 187, D3 (OPEN)
SUBCATEGORY
1- Uncategorized: Attribution for review and category validation
2-AHJ: City or County Requirements
3-ELECTRICAL TECH (ET): Human Error
4-DESIGN: Incorrect Design, AB Design Process
5-INSPECTION: Schedule confirmation, Missing or incomplete required documentation
6-CUSTOMER
Data Source: Salesforce/EVV, 6/22/2026 Owner: RLJ QA Support: ZJW, TGM

## Slide 15
SPWR Direct S14 Final Inspection Verified Pareto, WW18-WW25
Data Source: Salesforce/EVV, 6/22/2026 Owner: RLJ QA Support: TGM, ZJW
2ND LEVEL PARETO BY CREW

## Slide 16
SPWR Direct S14 Final Inspection Verified Pareto, WW11-WW18
Data Source: Salesforce/EVV, 5/11/2026 Owner: RLJ QA Support: TGM, ZJW MEMO ZJW-30A
Chart: PARETO ANALYSIS BY FIELD CREW
| IL ET | MI ET | CA crew 2 | OR ET | OH ET | MD ET | NV crew 3 | CO crew 1 | CO crew 2 | OR crew 1 | WA ET | WA crew | NV crew 3 | NC ET | WI ET
N | 15 | 8 | 6 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
%Cumulative | 0.31915 | 0.48936 | 0.61702 | 0.70213 | 0.76596 | 0.80851 | 0.82979 | 0.85106 | 0.87234 | 0.89362 | 0.91489 | 0.93617 | 0.95745 | 0.97872 | 1
BASELINE

## Slide 17
SunPower Direct M2 Corporate QA Inspection, WW25
Author: RJG/EVV, 6/20/2026
Owner: KMM/AEP
SPEC 12445
RCCA 234, D3
(OPEN)
Spec: 12445
97%
Escalate to
SSB
THIS IS CANDIDATE FOR ANDON CORD

## Slide 18
SunPower Direct M2 Corporate QA Inspection, WW25.5
Author: RJG/EVV, 6/20/2026
Owner: KMM/AEP
SPEC 12445
RCCA 234, D3
(OPEN)
Spec: 12445
97%
Escalate to
SSB
THIS IS CANDIDATE FOR ANDON CORD

## Slide 19
SunPower Direct M2 Corporate QA Inspection, WW24-WW25
Spec 12445
RCCA 234. D1
(OPEN)
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Incorrect Shine Disclosure (FUNDING)

## Slide 20
SunPower Direct M2 Corporate QA Inspection, WW24-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Spec 12445
RCCA 234. D3
(OPEN)
TGH – Tyson Hunter, LTD – Leo Miguel De Perio

## Slide 21
SunPower Direct M2 Corporate QA Inspection, WW19-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Spec 12445
RCCA 234. D3
(OPEN)
2 – Request new Shine Disclosure (FUNDING)
2 – Incorrect Shine Disclosure (FUNDING)

## Slide 22
SunPower Direct M2 Corporate QA Inspection, WW19-WW25
Author: RJG/EVV, 6/22/2026
Owner: KMM/AEP
Spec 12445
RCCA 234. D3
(OPEN)
TGH – Tyson Hunter, LTD – Leo Miguel De Perio
JDH – James Hampton, PXB – Pallavi Bhasker

## Slide 23
Author: EVV, 6/16/2026
S5: SPWR Direct Permit Pack Complete QA FPY
Owner: SGS/BCB QA: DJF
97%
Escalation
to SSB
RE-INTORDUCE PERMIT PACK QA
REVISE PERMIT PACK QA TO REFLECT THE CORRECT PROCESS
TRAIN AND DEPLOY PERMIT PACK QA TO DESIGN TEAM
QUALITY AUDITS AGAINST THE SPEC
REVIVE THE FPY OF ENPHASE DESIGN
Specs L2: 12777 Specs L4: 12385

## Slide 24
Spec 12385
Author: EVV, 6/16/2026 Owner: SGS/BCB QA: DJF
Specs L2: 12777 Specs L4: 12385
S5: SPWR Direct Permit Pack QA Pareto
START WITH DESIGN DEFECTS FOR Q2 FROM FUNDING (M1 & M2)
PULL DATA FROM SALESFORCE BASED ON LAYOUT AND UPGRADE REVIEW

## Slide 25: NEW HOMES PROCESSES: TARGET TO FPY=100%
T Level | Stage | Process Owner/Quality | Milestone1 | to | Milestone2 | Level 2 | Level 3 | RCCA | LATEST FPY
T0 | C1 | SFA/RJG | Community Lead | to | Community Bid Request | 12321 | 10508 | 145, D6 | Investigating*
T0 | C2 | SFA/RJG | Community Bid Request | to | Community Bid Review | 12321 | 12507 |  | Investigating*
T0 | C3 | SFA/RJG | Community Bid Review | to | Community Award | 12321 | 12507 |  | Investigating*
T0 | C4 | MTO/TGM | Community Award | to | Final Design Approved | 11227 | 11463 |  | 100%
T0 | C5 | MQT/TGM | Final Design Approved | to | Production Trench | 13051 | 12507 |  | Investigating*
T1 | L6 | RIH/TGM | Production Trench | to | Lot Design Requested | 13044 | 10549 | 154, D8 | Investigating*
T1 | L7 | MTO/TGM | Lot Design Requested | to | Lot Design Completed | 11229 | 11466 | 154, D8 | 100% (WW21)
T1 | L8 | JMN/ZJW | Lot Design Completed | to | Lot Permit Approved | 11287 | 10506 | 150, D6 | Investigating*
T1 | L9 | RIH/ZJW | Lot Permit Approved | to | Rough Wire | 13044 | 10791 |  | Investigating*
T2 | L10 | RIH/TGM | Rough Wire | to | Install | 13044 | 10790 |  | Investigating*
T2 | L11 | ROS/TGM | Installation | to | Job Close Out (JCO) | 12752 | 10790 | 161, D6 | 100% (QC)
T3 | L12 | RIH/ZJW | Job Close Out (JCO) | to | Final Permit Approved | 13044 | 12327 |  | Investigating*
T4 | L13 | LKR/EZD | Final Permit Approved | to | Permission To Operate (PTO) | 12281 | 10853 | 148, D6 | 100% (CQA)
T5 | L14 | KAM/EZD/TGM | Permission To Operate (PTO) | to | Activation | 13058 | 12152 |  | Investigating*
T0 | C15 | RIH/EZD | Model Trench | to | Community Install Complete (Parallel) | 13044 | 11971 |  | Investigating*
T1 | L16P | LMR/RJG | Opportunity appt. confirmed | to | HO Contract Signed (Parallel) | 13037 | 10782 |  | Investigating*
T1 | L17P | PPV/RJG | HO Contract Signed | to | Escrow date (Parallel) | 13066 | 10670 |  | Investigating*
T2 | L18P | PPV/RJG | Job Close Out (JCO) | to | Escrow date (Parallel) | 13066 | 10670 | 148, D6 | Investigating*
T2 | L19P | LMR/RJG | Escrow date | to | TPO Contract Signed (Parallel) | 13037 | 12477 |  | Investigating*
T4 | L20P | AEP/RJG | TPO Contract Signed | to | M1 -Installation (Financier Approval) (Parallel) | 12752 | 10724 | 228, D4 | 100% (CQA)
T4 | L21P | AEP/RJG | M1 | to | M2 -Activation (Financier Approval) (Parallel) | 12752 | 10808 | 224, D6 | 100% (CQA)
Author: JYH/EVV/ERF, 5/30/2026
Owner: ERF
Spec: 10009
1 – PREVIOUS WEEK
2 – MONTHLY CADENCE
3 – ALBATROSS DATA ONLY
4 – PENDING SIGNOFF
5 – SPEC FOR UPDATE
* Salesforce Data gathering